Task	Duration (Day)	Predecessors
A	3	-
B	4	A
C	2	A
D	5	B
E	1	C
F	2	C
G	4	D, E
H	3	F, G

Delivery Date: after 21 days.
Tasks could be delayed without delaying the schedule: none.