Task ID	Activity	Predecessors	Duration (month)	Budget (K$)	Progress	AC (Actual Cost)
1	Preparation	-	2	600	100%	600
2	Design	1	3	1200	100%	1400
3	Implementation	2	2	400	50%	200
4	Testing	2	3	1200	33.3%	500
5	Deployment	4	3	300	0%	0

By how much is over / under budget? 700 K$ under budget.
By how many days is it ahead / behind the schedule? Tasks on time.
By the end of the project, by how much will it be over / under budget? Approximately, 700 K$ under budget.